## Sheet1
Preparation	Quote Submission	Planning	Layout	Content Preparation	Content Integration	Design	Functionalities	Technical and Usability	Testing (first round)	Going Live	Training of staff	Marketing and SEO	Testing (second round)	Launch	Maintenance and Optimization	Management Processes
Job specificities	Confirmation of site objectives	Website Title	Overall look and feel	review content providers (writers, illustrators, etc)	Merge mockup and conten	Artworks reception/ update/ creation (photos, illustrations, etc)
appraisal of existing websitesor IT Systems	choose business model and marketing plan	Host selection and registration	choose fonts	text reception/ update/ creation	Pay special attention to content layout and hierarchy (try to meet the user “Z” reading pattern)	Logo reception/ update/ creation
check competition	plan interactions, technologies and functionalities	Mirrors and other domain-related registrations	color scheme research	art reception/ update/ creation (photos, illustrations, etc)	define headers (h1, h2, etc) and paragraphs	Design header with clear statement of the site purpose and prominently placed logo linked to home page
Site goals and overall strategy	choose content management system	website structure and information architecture	Make sure your color scheme is accessible to colorblind and visually impaired people (or provide alternatives	add web specific content (text, art, music, etc)	adapt font size, leading, spacing...to improve legibility	add visible search form to the header or to top of right column
web design client questionnaire	choose data delivery model and backup	validate wireframe	Standards and templates (usability, accessibility, etc)	distribute content quantity – keep homepage light and effective	Choose if you want to allow/disable text to be resized through the browser	design clear navigation (if in JS or flash, provide a text-based alternative)
	roles and responsibilities		basic layout creation (x)html/css	provide a call to action to every page (avoid dead ends)	identify and add meta tags, meta descriptions and descriptive titles	design main section (columns and sidebars) and footer now or later
	initial timetable		validate mockup	copyrights, terms of use, and privacy policy	Label links with anchor tags which show where they lead	Make sure that important content is above the fold at least for home page
	Quote Submission			contact details	make links with anchor tags which show where they lead	balance illustrations/ photo and text importance according to the site purpose
	project validation and deposit paid			about page (with author(s), company info, credits, etc)	make links consistent and easy to identify (style, special links, like feeds or emails)	Advertising-ready design and link page set-up
				testimonials, reviews and awards	add “alt” tags on all significant images (keep “alt” tags empty on other images)	design visible testimonials, reviews and awards
				products description	Provide text-based alternatives for all significant medias without “alt” tags	make sure content and/or design elements encourage future visitation or viral sharing
				FAQs		make sure company information and contact (email or form) are immediately accessible (address, phone number, etc)
				other content		make choices do not become cumbersome for clients/visitors/ users
				optimize target keywords usage in content		style lists
				proofread
				validate content (if you provide site copy)